## Task Breakdown
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Establish design system and fonts | 2025-03-18 | 2025-03-18
2 | Create task and user story lists | 2025-03-18 | 2025-03-18
3 | Design an initial version of all pages | 2025-03-18 | 2025-03-18
4 | Implement the home page | 2025-03-18 | 2025-03-18
5 | Implement the header | 2025-03-18 | 2025-03-18
6 | Implement the Groups page | 2025-03-24 | 2025-03-25
7 | Implement the Gift Shop | 2025-03-24 | 2025-03-25
8 | Implement the About page | 2025-03-27 | 2025-03-25
9 | Make pages highlight | 2025-03-27 | 2025-03-25
10 | Implement a lightbox system | 2025-03-27 | 2025-03-25
11 | Make forms with lightboxes | 2025-03-27 | 2025-03-27
12 | Add content for various other pages | 2025-03-27 | 2025-03-25
13 | Add social links in the footer | 2025-03-30 | 2025-03-30
14 | Complete Design Map & Summaries | 2025-03-30 | 2025-03-30
15 | Complete user testing & interviews | 2025-03-30 | 2025-03-30
...